| DC&SDC Local Development Plan 2032 (LDP) Timetable for LDP Plan Strategy HMO Revision (PS-R) – JULY 2026* |  |  |
| --- | --- | --- |
| Estimated Timescale (Tasks per Month / Quarter) | LDP PS Revision Stage | Sustainability Appraisal (SA) & Associated PS-R Tasks |
| April - June 2026 | Agree PS-R process, scope and terms for the defined HMO Revision of LDP Plan Strategy (PS) |  |
| May-July 2026 | Agree / Publish LDP PS Revision Timetable (& Revised Statement of Community Involvement) |  |
| May & June 2026 | Prepare Evidence in support of HMO Revision Formally Advertise Commencement of PS Revision | Scoping for SA, HRA, EQIA & RNIA |
| June 2026 | Member & Stakeholder Engagement |  |
| July 2026 August & September 2026 | Cttee / Council agree & Publish PS Revision POP -Preferred Options Paper (POP) Statutory Public Consultation 8 weeks | Publication of Scoping Report(s) |
| October 2026 October & November 2026 December 2026 & January 2027 | Publish draft PS Revision (dPS-R) Statutory Public Consultation: 8 weeks for Representations; 8 weeks for Counter Representations | Publication of SA Interim Report (incorporating SEA) Publication of draft EQIA Report |
| Feb / March 2027 April / May 2027 | Submit dPS-R documents to DfI, DfI Assess & Forward to PAC / Other Body | Any Addenda re. dPS-R Changes? |
| September 2027 | Assess PS-R, organise & advertise the IE Hold the dPS-R Independent Examination (IE) |  |
| November 2027 January 2028 | IE Advisory Report to DfI DfI issues Binding Direction to the Council |  |
| February 2028 | Adoption of Revised LDP Plan Strategy (PS) | Public Consultation & Publish Final SA & Final EQIA reports |

Please note: This is an indicative Timetable and may be subject to change, particularly due to factors outside the control of the Council e.g. DfI and PAC/Others’ consideration or delays or legal challenges.

* Note that this Timetable for the Revision to the LDP Plan Strategy (PS-R) should be read in conjunction to the overall Timetable for the preparation of the LDP Local Policies Plan (LPP). Both processes will be proceeding in parallel.