Derry City and Strabane District PEACEPLUS Partnership Board

Meeting Date: 	Tuesday 7th March 2023

Time: 			10.00am – 11.30am

Venue:			St.Columb’s Park House, Derry~Londonderry.

AGENDA ITEM

1. Meeting Opening 1.1 Welcome and Apologies 1.2 Conflict of Interest 1.3 Minutes of previous meeting / Matters arising (p.3-7)

2. Management Update (Myriam & Sue) 2.1 Sue – Current work by team Team predominantly working on creating the detailed budget breakdowns and descriptions. Recruitment: 2 x new JD’s drafted, 3 existing JD’s updated. Skills match process by end March and JD’s to be finalized for all posts (including grading) in time for bid. Currently sitting with HR. N/S Ministerial council rep 20/2/23. TEO 27/2/23. Brief meeting set by SEUPB for 30th March. OJEU – SEUPB response to work with CPD – implications for audit risk. GDPR training. 9/2/23 online initial testing of JEMS – looks like a lot of detail in annexes and workplans. We’ve put forward our suggested Work plan spreadsheet Annex template for feedback. Destruction of PEACE III materials (retention complete). Exploring options for PEACEIV storage. Expecting final PEACEIV Audits soon – on claims submitted Jan 22. Bid content ratified by council. 2.2 Steering Groups See Appendix C for list of Board members on each Steering Group. Each group will have a chair – elected annually (Does Board wish to hold off on that until October after new Chair/Co-Chair elected in September and after local elections?) Quorum is 4. Key role at this point will be working through draft tender specifications and having more in depth awareness of the projects under their theme. Any offer of a free venue to host CRT (Cityside) Steering group other than DCSDC? For Decision: Board view on when Chairs are elected for Steering Groups. In person meetings? 2.2 Myriam – Update on management at Programme Level /Overall process/ schedule. 2.3 Myriam – Update on current work on bid

3. Communications Update (Sue) 3.1 Press, Social Media, Web & E-zine: Not a current focus. Will update web and sort publication of bid in due course – likely when bid has been submitted. Possible small event to in person pre-summer to update the C&V sector on timescales, content and opportunities. Discussion: Board thoughts on Communication with C&V sector event? Happy that details are agreed with relevant steering group.

4. Key Business: (Mary Claire & Sue) 4.1 Example of Workplan (draft) – Mary Claire (Annex D) 4.2 Powerpoint on evaluation and monitoring thoughts – for discussion. 4.3 Next steps in Co-Design & update on draft application form. (Myriam & Sue) Focus will be on population Annexes and Application including detailed budget breakdown and outputs as well as Peace and Reconciliation content; finalizing JD’s; working on a tender spec ‘template’ with DCSDC procurement. Submission once available.

5. Meeting Closing 5.1 AOB 5.2 Date of Next Meeting: No April Meeting (Purdah / Easter). Steering groups in May. See Appendix B.

Derry City and Strabane District PEACEPLUS Partnership Board

Minutes of Meeting

Meeting Date: 	Tuesday 7th February 2023

Time: 			10.00am – 11.30 pm

Venue:			Fir Trees Strabane (And online hybrid option)

| Sue Divin | DCSDC | Christopher Jackson (online) | SF |
| --- | --- | --- | --- |
| Myriam Fearon | Fearon Consulting | Philip McKinney (online) | Alliance |
| Fiona Lafferty | DCSDC | Martin Reilly | SDLP |
| Mary Claire Kerlin | DCSDC | Maurice Devenney (online) | DUP |
| Conor Heaney | SF | Catherine Cooke | FWIN |
| Gerard Deane | Holywell Trust | Nikki Yau | FREF |
| Martin Duffy | Derg LGP | Ruairi McHugh(Online) | SF |
| Sharon Doherty | St Columb’s Park Recon Trust | William Calderwood | PSNI |
| Anne McTaggart | Youth Action | Paul Gallagher | Ind |
| Keith Kerrigan | DUP | Kyra Reynolds | BBI |
| Derek Moore | NW Cultural Partnership | Jackie Connolly | Ballyarnett LGP |
| Lisa Moore-Maguire | Foyleside LGP | Charles Lamberton | Moor LGP |
| Alison Wallace | Waterside LGP | Gus Hastings (online) | Faughan LGP |
| Claire Russell | Sperrin LGP | Marie Gallagher | DFC |
| Aodhán Harkin | Strabane LGP | Darren Guy (online) | UUP |
| Ciaran McLaughlin | DAERA |  |  |

- Meeting Opening

  - Apologies received from:  Drew Thompson, Brian Tierney, Noelle O Donnell, Mary O’Neill, Declan Norris, Noelle Donnell.

  - Conflict of Interest - The chairperson reminded members of Conflict of Interest and their responsibility to declare throughout the meeting where relevant.

  - Minutes of Previous meeting/Matters arising -  Board meeting of 10th January 2023 were held to be an accurate record.

Proposed:  Aodhán Harkin			Seconded:  Claire Russell

2. Management Update

Myriam took members briefly through a presentation from Blue Zebra on the Peace Plus bid and the indicative content required for the bid.  No comment from Board members.

- 2.1 Update at Programme Level (SEUPB)

- Sue informed members that the Cyber security requirements for the PEACEIV Programme for electronic invoices is ISO 27001. All council in NI (to the best of our knowledge are NOT working to that accreditation but have instead adopted the ‘Cyber Essentials Plus’ accreditation as the relevant target. She has emailed SEUPB about this to see if they could consider allowing this accreditation in their programme rules so that all NI councils will not face the complexity of Director sign offs for all electronic invoices and physical retention of documentation for 7 years after the end of the programme. As well as physical space, it would save roughly £10K if electronic document retention was possible.

- A PEACEPLUS Partnership Development Report has been submitted to BluZebra (for SEUPB Process)

- A PEACE Managers online meeting with SEUPB took place on the 26th January 2023.  Sue informed members that there is movement from Westminster and it is hoped that the Monitoring Committee will sign of the programme in March with a launch in April. There will be a 6 month window for submission of the plan to SEUPB.  Derry City and Strabane Council will submit their plan in April with a 22 week turn around and hopefully a Letter of Offer in October.

- As of yet there are no templates developed for the Annexes of the plan but SEUPB have welcomed input from the Team.  They have also extended the word count on the application form.

- At present there is user testing on the new JEMS system which is replacing the existing EMS system used in Peace IV.  A meeting with SEUPB on this system is on 9 January 2023 with the Peace Plus team to test out scenarios.

3. Communications Update (Sue)

- 3.1 Press, Social Media, Web & E-zine:  Sue updated member on the communication provided by Peace Plus which is as follows:- Ezine issued in January –indicated summary of Board decisions for District projects. Also issued to LGP’s. Updated web with minutes.

- 3.2 Communications Plan & Communications Crisis Plan

Sue informed members that as part of the Peace Plus Action Plan a communication/crisis plan must be in place.  A template that was used under Peace IV was updated accordingly by Sue and relevant information was added.  The board was asked if they were happy to approve the said plan.

Decision: Communications Plan and Crisis Communications Plan approved by Board.

Proposed:  Catherine Cooke			Seconded:	Martin Duffy

- 3.3 Publication of PEACEPLUS Action Plan (at least on website in accessible form)

Members were made aware that once the Peace Plus Plan has been completed and submitted it will be accessible via the website. This will be actioned later in the Spring.

4.	Key Business: (Myriam & PEACE Team)

4.1 Final Feedback from Questionnaire (Myriam)

Members were informed that the PEACEPLUS Questionnaires closed on the 6th February 2023 and there was a total of 1535 responses.  Myriam took them through an analysis of the responses and the support of the projects per DEA and Thematically.  The Board were content with the information.

4.2 Structure for Board & Steering Groups going forward? (Sue)

As we move from Co-design to management & delivery phase the PEACE Team are recommending the Board consider steering groups. The purpose of this is to streamline the tender’s procurement process. It may also help manage conflict of interest.   A breakdown of the Steering groups by participant targets and no of projects was provided to the Board.  Sue explained the role of each steering groups per theme as well as the role and function of the operational steering committee. In particular, it was suggested that Steering groups could help to manage/minimise any potential  conflicts of interest issues during the procurement phase of the programme as draft tender specifications etc will not be circulated electronically. It was suggested that Board members try to select the Steering Group for the theme for which they are likely to have least conflicts of interest. Terms of reference for the steering groups were available to the Board to scrutinise.

Sue gave 2 options to the board as follows:-

Option A: Bi-monthly Board meeting and bi-monthly 3 steering groups (alternate months).

Option B: Continue with monthly full Board meeting and no steering groups.

Sue also suggested that within the CRT Steering groups and because it had less projects under it than the other Steering Groups that communications and management would be included under this group.

The Board sought some clarifications. It was confirmed it would still be one meeting per month only with either option. Issues around Quorum issues with steering groups in PEACEIV were discussed – it was felt there were enough members on each steering group for it to function, but this can all be reviewed if necessary. It was clarified that members could self-nominate the steering group of their choice – assuming that there was a bit of flexibility to ensure a spread of representation across the 3 groups. There was a lot of agreement that it made sense to try the steering groups system.

Members agreed to go with Option A – Bi-monthly Board meeting and bi-monthly 3 steering groups (alternate months).  Members were also happy to include communications and management under the CRT Steering group.

A form was circulated for members to add their name to the preferred Steering Group.  It was anticipated that there would be between 10 and 12 members on each group.  Given that not all members were present at the meeting, it was agreed that Sue would finalised the nominations electronically and circulate once completed.

Action: Sue to finalise nominations electronically and circulate final version to Board members.

Decision: The Board agreed to adopt 3 Steering groups and monthly meetings will rotate bi-monthly with Full Board meetings. This can be reviewed if neccessary at a later date.

Proposed:	Catherine Cooke			Seconded:	Anne McTaggart

.	4.3 Draft schedule for meeting dates – dependent on decision on steering groups.

Members were asked to agree a draft schedule for future meetings to include Board and Steering groups based on Option as detailed below:-

Option A Board & Steering Groups

Board: Tuesday 7th March 10am

April – no meeting due to Purdah & local council elections on 18th May 2023 & Easter. June/July elected members’ annual nominations. Current elected members stay until then.

May Steering Groups

June Steering Groups

Board: Tuesday 12th September 10am (moved generally to 2nd Tuesday)

4.4  Traffic Lights – Thematic presentation & Procurement Schedule

The traffic lights are now set up by the 3 themes SEUPB use under Theme 1.1. The Peace Team took members through a proposed timeframe of when projects would be advertised (Procurement Schedule) between September 2023 and December 2024.  The team took into consideration the following elements:

For discussion - listed broadly by priority contracting schedule. Prioritised by:

- Realistic workload for team

- 3 year & capital projects, Larger budget / larger set up time

- Duration of project / Urgent need

- Spread across district

- Youth availability in summer

- No DCSDC tenders in August

- Potential need for some re-advertisements

- Hope that Phase 5 could be brought forward if possible with workloads

- Management side of programme builds as time passes.

Decision (by consensus): The board was content with the priorization and draft schedule.

Sue also informed members that she was working on Job Descriptions for the Peace Plus team and that the other 2 members of staff would not be recruited until a letter of offer was received.

4.5 Update on CRT Historic Cemeteries

- Noting for Board information that the budgets within this project have been revised following discussion with the relevant staff. The overall budget £250K and 275 participants remains the same. The internal split however is now £120K on capital and £130K on Programmes.

Decision (by consensus): The board were content that this was OK.

4.6	Next steps in Co-Design & update on draft application form.

February / March: Work on SEUPB application form ready for submission. Drafting JD’s. Budgets. Procurement Plan. GAANT delivery chart. Final PEACEIV Audits, payments, shifting files to storage.

March Board: Management Plan (Including consideration of Evaluation & Monitoring.)

April: Probable submission of application (dependent on SEUPB).

April onwards: Drafting Tender Specs. Progressing on Evaluation & Monitoring systems

5.0  	Meeting Closing

5.1  AOB Reminder any social partner expenses claims need submitted within the financial year

Date of Next Meeting: Tuesday 7th March 10am – 12 noon. (Waterside venue TBC)

Appendix A: Board Member’s Attendance 2022/23

| Statutory Pillar |  | 10/5 | 21/6 | 6/9 | 4/10 | 8/11 | 6/12 | 10/1 | 7/2/23 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| William Calderwood (d. Shannagh Farren) | PSNI | x | x | x | x | x | x | x | x |
| Deborah Cross (d. Declan Gallagher) | EA | x | x |  | x | x | x |  |  |
| Marie Gallaher (d. Sharon McCullagh) | DfC | x |  |  | x |  | x | x | x |
| Mary O'Neill (d.Noel McNulty) | NIHE | x | x | x | x | x |  | x |  |
| Seamus Ward (d.Bronach McMonagle) | WHSCNI | x |  | x | x |  | x | x |  |
| Ciaran McLaughlin (d. Gerard O’Neill) | DAERA | x |  |  |  |  |  |  | x |
| Social Partners – Local Growth Partnerships |  |  |  |  |  |  |  |  |  |
| Jacki Connolly (d.Darren Kirby) | Ballyarnett | x | x | x | x | x | x | x | x |
| Martin Duffy (d. Andy McKane) | Derg | x |  | x | x |  | x | x | x |
| Aodhán Harkin (d.Ursula Doherty) | Strabane | x |  | x |  | x | x | x | x |
| Gus Hastings (d.Martin McCartney) | Faughan |  | x |  | x | x | x | x | x |
| Charles Lamberton (d.Seamus Breslin) | Moor | x | x | x |  | x | x |  | x |
| Claire Russell (d.Patricia McNulty) | Sperrin | x |  | x | x | x | x | x | x |
| Alison Wallace (d.Geraldine Doherty) | Waterside | x | x | x | x | x | x | x | x |
| Lisa Moore-Maguire (d. Jim McColgan) | Foyleside | x | x | x | x | x | x | x | x |
| Elected Representatives Pillar |  |  |  |  |  |  |  |  |  |
| Conor Heaney | SF | x |  | x |  |  | x |  | x |
| Christopher Jackson | SF | x | x | x |  | x | x | x | x |
| Ruairi McHugh | SF |  |  |  | x |  |  | x | x |
| Declan Norris (from December 2022) | SDLP |  |  |  |  |  | x | x |  |
| Maurice Devenney | DUP |  | x | x | x | x | x | x | x |
| Keith Kerrigan | DUP |  | x | x |  | x | x |  | x |
| Darren Guy | UUP | x | x | x |  | x | x | x | x |
| Philip McKinney | Alliance |  | x |  | x | x | x | x | x |
| Martin Reilly (from July 2022) | SDLP |  |  | x | x | x | x | x | x |
| Paul Gallagher (from July 2022) | Indep |  |  |  |  | x | x |  | x |
| Brian Tierney (from July 2022) | SDLP |  |  | x | x | x | x | x |  |
| Drew Thompson (from July 2022) | DUP |  |  |  | x |  | x | x |  |
| Social Partners Pillar |  |  |  |  |  |  |  |  |  |
| Gerard Deane (d. Fiona Corvan ) | Holywell | x | x |  | x | x | x | x | x |
| Catherine Cooke (d. Bethany Moore) | FWIN | x | x | x | x | x | x | x | x |
| Sharon Doherty (d. Michelle Simpson) | St.CPH | x | x | x | x | x | x | x | x |
| Noelle Donnell (d. Sinead Barr) | H’bird | x | x | x | x | x |  | x |  |
| Anne McTaggart (d. Dominic Bonner) | YANI |  |  | x | x | x | x |  | x |
| Derek Moore (d. Kyle Thompson) | NWCP | x | x | x | x | x | x | x | x |
| Kyra Reynolds (d. Rachel Mullan-Carlin) | BBI | x |  | x |  |  |  | x | x |
| Nikki Yau (d. Agnieszka Luczak) | FREF | x | x | x | x | x | x | x | x |

Appendix B: PEACEPLUS Timetable of meetings for Board & Steering Groups

|  | Mar 23 | Apr 23 | May 23 | Jun 23 | Sept 23 | Oct 23 | Nov 23 | Dec 23 | Jan 24 | Feb 24 | Mar 24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEACEPLUS Board (Wk 2 Tuesdays) | 7th | - | - | - | 12th | - | 14th | - | 9th | - | 12th |
| CRT (Cityside Wk 2 Tuesdays. DCSDC Strand Rd Offices, level 5) | - | - | 9th Level 5 | 13th Level 5 | - | 10th | - | 12th | - | 13th (or 6th?) | - |
| TPC (Strabane Wk 1 Wednesdays Glenelly or Function Rm, Strabane DCSDC Office) | - | - | 3rd Glny | 7th Glny | - | 4th Glny | - | 6th TBC | - | 7th | - |
| BRCI (Waterside Wk 2 Thursdays. Shared Future Centre) | - | - | 11th SFC | 15th SFC | - | 12th SFC | - | 14th SFC | - | 8th SFC | - |

*No meeting April 2023 due to Easter & Purdah for Local Council Elections

** No Board or Steering Group Meetings July or August

Appendix C - Nominations to PEACEPLUS Steering Groups

| CRT Community Regeneration & Transformation, Management and Communications. | TPC Thriving and Peaceful Communities. | BRCI Building Respect for Cultural Identity. |
| --- | --- | --- |
| Venue: Cityside | Venue: Strabane | Venue: Waterside |
| Day/Time/Week: Tue am Week 2 of month | Day/Time/Week: Wed am Week 1 of month | Day/Time/Week: Thurs am Week 2 of month |
| 1 Ciaran McLaughlin (DAERA) | 1 Marie Gallaher (DfC) | 1 Deborah Cross (EA) |
| 2 Mary O’Neill (NIHE) | 2 William Calderwood (PSNI) | 2 Seamus Ward (WHSCNI) |
| 3 Gerard Deane (Holywell) | 3 Noelle Donnell (Hummingbird) | 3 Catherine Cooke (FWIN) |
| 4 Kyra Reynolds (BBI) | 4 Anne McTaggart (YouthAction NI) | 4 Sharon Doherty (St.Columb’s Pk House) |
| 5 Derek Moore (NWCP) | 5 Alison Wallace (Waterside DEA) | 5 Nikki Yau (Migrant Centre NI) |
| 6 Charles Lamberton (Moor DEA) | 6 Lisa Moore-Maguire (Foyleside DEA) | 6 Martin Duffy (Castlederg DEA) |
| 7 Aodhán Harkin (Strabane DEA) | 7 Gus Hastings (Faughan DEA) | 7 Jacki Connolly (Ballyarnett DEA) |
| 8 Paul Gallagher (Independent) | 8 Claire Russell (Sperrin DEA) | 8 Christopher Jackson (SF) |
| 9 Conor Heaney (SF) | 9 Darren Guy (UUP) | 9 Philip McKinney (AP) |
| 10 Drew Thompson (DUP) | 10 Ruairi McHugh (SF) | 10 Maurice Devenney (DUP) |
| 11 Brian Tierney (SDLP) | 11 Keith Kerrigan (DUP) | 11 Martin Reilly (SDLP) |
|  | 12 Declan Norris (SDLP) |  |

| Free Choice | Statutory Partners | Social Partners (Open Call) | LCGP Partners | Elected Representatives |
| --- | --- | --- | --- | --- |

# Text boxes

Appendix D:

Example of 1 project set out at the level of detail we think may be required.

SEUPB will hopefully give us some feedback.

They many need more detail than this.