Derry City and Strabane District Peace IV Partnership Board

Meeting Date: 	Tuesday 9th March 2021

Time: 			10.00am – 11.00am

Venue:			Zoom Online Meeting

| AGENDA ITEM | PAPERS |
| --- | --- |
| 1. Meeting Opening (Chair Alison Wallace/Co-Chair Cllr Martin Reilly) 1.1 Welcome/Apologies (Chair/Co-Chair) 1.2 Declarations of Interest (Chair/Co-Chair) 1.3 Minutes of previous meeting / Matters arising (Chair/Co-Chair) | Minutes p.2-11 Board Report p.12 |
| 2. Update from Peace IV Secretariat 2.1 PIV Team March Update (Sue) 2.2 Finances Update and Underspend (Sue/Jennifer) | Board Report p.12-13 |
| 3. Update on Operational Workplans (Chair Cllr Martin Reilly) 3.1 Workplan 1: Project Mobilisation/Management (Sue) 3.2 Workplan 2: Communications (Sue) 3.3 PEACE PLUS Update (Sue) | Board Report p.13-14 |
| 4. Update on Children and Young People (Chair Margaret McLaughlin) 4.1 Key issues (Sue) 4.2 Project Officer Update: (Mary Claire & Fiona) | Board Report p.15 |
| 5. Update on Shared Spaces and Services (Chair Cllr C.Jackson) 5.1 Key issues (Sue) 5.2 Project Officer Update: (Mary Claire & Fiona) | Board Report p.16 |
| 6. Update on Building Positive Relations (Chair Derek Moore) 6.1 Key issues (Sue) 6.2 Project Officer Update (Mary Claire & PIV Team) | Board Report p.16-17 Appendix C - Riverine |
| 7. Meeting Closing 7.1 Any Other Business 7.2 Review of Actions (Jennifer) 7.3 Date of Next Meeting | Board Report p.17 |

Derry City and Strange District Peace IV Partnership Board – 12th Jan 2021

Minutes of Meeting:

Meeting Date: 	Tuesday 12th January 2021

Time: 			10.00am – 10.55am

Venue:		Zoom online

1. Meeting Opening

1.1 Welcome & Apologies:

Attendees:

| Sue Divin | DCSDC | Wendy Gibbons | OWNRP |
| --- | --- | --- | --- |
| Jennifer Coyle | DCSDC | Catherine Cooke | FWIN |
| Fiona Lafferty | DCSDC | Gerry Deeney | NIHE |
| MaryClaire Kerlin | DCSDC | Alison Wallace | WNP |
| Kathleen McCaul | NWRC | Anne Mc Taggart | Youth Action |
| Derek Moore | LBF |  |  |

1.1 Apologies/ Welcomes:

Paul Gallagher TU, Ald Gillian Moss NWRC, Willie Lamrock YMCA, Teresa Stewart Strabane A.Y.E, Margaret McLaughlin Dennett, Chief Ins Rosie Thompson PSNI, Cllr Raymond Barr Independent, Cllr Aileen Mellon Sinn Féin, Cllr Steven Edwards SDLP, Agnieszka Luczak Polish Abroad, Bernie Melaugh western trust, Dairine McGarrigle  DFC, Ald David Ramsey DUP, Cllr John Boyle SDLP, Maureen Hetherington The Junction, Cllr Philip McKinney ALL, Cllr Martin Reilly SDLP, Kevin O’Connor DCSDC, Ald Hilary McClintock DUP, Cllr Sandra Duffy Sinn Féin, Cllr Christopher Jackson Sinn Féin, Cllr Ruairí McHugh Sinn Féin, Mark Gibney EA.

1.2 Declarations of Interest

Standing conflicts of interest noted for all meetings as standard:

Agnieszka Luczak - Cohesive Neighbourhood tender.

Alison Wallace - Interface tender, Waterside shared village tender, shared space

Maureen Hetherington – Patriarchy

Anne McTaggart – Marginalised Young Adults

Margaret McLaughlin – Shared Space Rebid.

Derek Moore - Cross-cultural tender.

Shaun Harkin – St Columb’s Park Interface Investment (Tullyally/Currynierin)

Ruairi McHugh – Castlederg GAA

1.3 Minutes

The minutes of the 10th November 2020 previous Board Meeting were held to be an accurate record.

Proposed:	Alison Wallace	Seconded:  Catherine Cooke

Action Agreed: As the meeting was not quorate, those present agreed that the minutes from 10th November 2020 and decisions taken at this meeting should be circulated to all Board members so that written responses could be noted to take the decisions to a quorate level.

1.4 Matters Arising:

Catherine asked what the situation was within Council now in relation to the upcoming centenary celebrations.  Sue explained that she had seen a number of news reports and added that as far as she was aware this seems to have been resolved within DCSDC at full committee.  She hadn’t heard anything official in council. Alison commented that yes she had also seen those reports and it looked as if the matter has been resolved.

2. Update from PEACE IV Secretariat – Functionality through Covid19

2.1 PIV Team Summer Update:

- Overview: Sue provided the Board with an update on what the PIV team are working on which is prioritising the ‘possible’. Projects are generally moving to an intensive completion and closing down phase. Sue highlighted that this requires extensive input from PEACE IV team in tying loose ends and final audit compliance before final payments can be released. Finances, statistics, end of project reporting, communications, and submission of cross-community contact spreadsheets etc are key elements.

Sue made the Board members aware that the more projects reach this phase the PEACE IV team will be increasingly limited in the support it can give to individual projects. There have been an additional 10 change requests since November bringing the total to 56. A small number of projects do still have not gone digital in delivery this is a concern and may lead to last minute underspend.

Sue explained that the latest lockdown means projects that had hoped for socially distanced delivery in Jan – March cannot do that. Further change requests or last minute underspends may ensue and workload on the team may hike because of this at a time when there are highly abnormal working conditions. Sue noted that the tendered projects will not underspend if they meet their contracted outputs but small grants and council led projects are a greater risk.

Sue advised that the PIV Team have worked to identify issues in advance and suggest alternatives to avoid underspend and continue to do so, but noted that we anticipate not having a clear picture on underspend until 31st March 2021. Sue added that the team also worked Nov/Dec to encourage key projects with capacity to finish/nearly finish pre-Christmas to focus on closing down. Sue explained that this effort was reasonably successful when strategically targeted and Increase in claims submitted and monitoring was noted.

- Communication with SEUPB: Sue explained that the major decisions from SEUPB are still slow. Sue highlighted that there has been reasonable contact with Case Officer, Garret McGinty and with Finance Officer, Catherine Murray – both extremely busy. Statistician is latest post to leave SEUPB. Sue advised that the formal addendum to contract to extend all of the PEACE IV programme has now been approved to Sept 2021 and signed off. Sue added that the EMS modifications completed on all 3 themes. A priority for the team is the continued to work on Claims, Audits, FLC’s and LP reports.

- Forward Focus: Sue noted that the next quarterly claim 19 is due at the end of January 2021. Sue made the Board aware that the financial forecasts will need redone and revised on EMS. A priority will also be for the team to focus on successfully closing down projects completed/nearing completion intensifies. Secondly, focus on intensive support for those projects not in a good position / with specific issues / potential underspend or inability to meet contracted outputs. The team will aim is to avoid cramming of project closures and payments in March 2021. Also focus on the Independent Evaluation process. Sue highlighted that it is likely at the March 2021 Board meeting there will have to consider the position at that point in time on unresolved issues such as underspend and incomplete projects.

2.2 Finances Update

Jennifer provided the Board members with a finance update on the following.

- Extensive progress on FLC and payments noting that we are now in a good position and up to date see details below in table.

- Minor hits on complex maternity/salary pay in relation to staff member ‘underspend’ can still be accessed via a Covid Change request.

- G.Corr Managing Authority Audit passed with no issues.

- Claim 19 is key area of work for January 2021.

- Expected request for financial forecasting from SEUPB imminent.

- Difficult to predict underspends from projects Board discussion in March 2021.

| Claim | £ Owed | Submission date: | Audit update: |
| --- | --- | --- | --- |
| Claim 16 (Jan – Mar 20) | £0 | Mid-May 2020 | CYP £ 184,494.20 Paid Dec 20 (Minor hit £2K) SSS £ 103,754.47 Paid Dec 20 BPR £ 233,936.87 Paid Oct 20. |
| Sub-claims 15.2 | £0 | Early Aug 2020 | Paid Dec 20 £48,232.25 |
| Claim 17 | £35,691.04 | Early Aug 2020 | CYP £35,691.04 FLC Received. (Minor hit £1.9K) LP submitted SSS £71,134.69 Paid Dec 20 BPR £199,886.62 Paid Dec 20 |
| Claim 18 | £273,352.63 | 3rd Nov 2020 | CYP £117,208.54 Audit sample returned. LP to do SSS £50,891.69 Audit sample returned. LP to do BPR £105,252.40 Audit sample returned. LP to do |
| Claim 19 |  | Due 31 Jan 21 |  |
| OWED: £309,043.67 |  |  |  |

3. Update on Operational Steering group

3.1 Workplan 1: Project Mobilisation/Management

Official Extension: Sue advised that the PEACE IV programme now runs to end September 2021 confirming that the new LOO received and signed.

Start and End surveys: Sue explained that the summarised Stats are below. Highlighting that positive progress has been made focus on end surveys.

| Theme | 4-1-21 Start Surveys | 4-1-21 End Surveys | Overall Target | Cross-Comm Balance CNR/PUL/Other |
| --- | --- | --- | --- | --- |
| C&YP | 2224 (108%) | 1088 (53%) | 2060 | 53%/28%/19% |
| SS&S | 1632 (130%) | 1041 (83%) | 1260 | 55%/26%/19% |
| BPR | 2248 ( 145%) | 1364 (88%) | 1548 | 45%/30%/25% |
| TOTAL: | 6104 (125%) | 3493 (72%) | 4868 | 51%/28%/21% *CBU 57%/33%/10% |

Traffic Lights: Sue explained that the Traffic lights spreadsheet has now been updated payments, progress, and participant numbers. Areas in red are of concern.

Independent Evaluation: Sue made the Board aware that Rubicon have now been appointed to complete the independent review. Extensive evaluation info passed to Peter Osborne and team have had initial meetings. Sue asks the Board to please attend the Board Session. Staff had separate session.  Timescale for this is for completion by June 2021 which includes a presentation at our closing event.

| Time | Date | Strand | Link |
| --- | --- | --- | --- |
| 10.30am | Tue 19th Jan | BOARD (Past and present) | Join Zoom Meeting https://zoom.us/j/97548883113?pwd=eDEvLzFjRk15UCtGcU52RVJETjY0Zz09 Meeting ID: 975 4888 3113 Passcode: 636131 |
| 10.30am | Wed 13thJan | Children & Young People | https://zoom.us/j/99839435496?pwd=dTFGRTYwU2c0N3RFRjh6YVo5MzNndz09 |
| 2.30pm | Wed 13thJan | Shared Space | https://zoom.us/j/97938178118?pwd=eTkxWGtKZ3BSQzg2UW9vcFhzbVpyUT09 |
| 10.30am | Thursday 14thJan | Building Positive Relations | https://zoom.us/j/97532229379?pwd=cEt5NkQyU0l1cWVIa1U3bUxlUGsvZz09 |
| 2.30pm | Thursday 14thJan | Small Grants | https://zoom.us/j/98378676668?pwd=Q3FUM1ovUmNEajNXSTRPTGtacHVIUT09 |

Statistics/Evaluation and Monitoring:  Sue advised the Board that the statistician situation has become challenging with the NISRA ‘Hub’ turning down full requirement as it was too much work over sustained period. NISRA offered to do end/close down process if handed statistically robust information. Interim service procured and contracted to achieve this. PIV manager will have to continue liaison with groups/monthly updates but overall high level statistical service is almost secured. Sue highlighted that the timescale for NISRA is set for April/May so all projects without exception must have completed evaluation and monitoring by 31st March 2021.

3.2 Workplan 2: Communications

Networking: Sue explained that the ‘Closing Down Clinics’ where held on 8th January with 23 participants attending and 15th December with 8 participants attending. The focused on key messaging for projects to successfully close down.

Videos: Sue noted that there are 3 final thematic videos being produced by from Pillarpix. 2 have now been completed and we are hoping that the final 1 will be completed soon.

Communications with projects: Ongoing and continuing emails to projects promoting key messages.

Press: Sue explained that the PIV press has been limited coverage from any projects or ourselves. Encouraging projects to still issue traditional press releases but also accepting online press if tagged appropriately to meet contract requirements.

E-newsletter: Sue added that November and December e-zines is now issued.

Magazine: Sue made the Board aware that the Double ‘2020 Covid’ printed issue magazine is now completed and has been distributed in December 2020.

Final Closure Event: Sue stated that in the March Board meeting we should be considering what format the final closing event should take. Noting that May 2021 is the likely time for this. The 3 thematic videos and findings of independent evaluation as well as setting scene for PEACE Plus are the likely focus.

3.3 PEACE PLUS Update

Sue advised that has communicated to Council CEO’s that the PEACE PLUS process is at Statutory Public Consultation stage. Then follows approval by the Northern Ireland Executive, the Irish Government and final submission to the European Commission for their approval. Sue highlighted that we are lucky in DCSDC area as we have strong Community Planning structures in place.

- Strong emphasis on community planning (plans and structures) along with heavy emphasis on cross-community/diversity/inclusion and sustained cross-community engagement.

- Overarching areas for content: ‘support social inclusion, build positive relations and improve the physical and social environment’ with 3 areas:

- Delivering community regeneration, empowerment, leadership, reimaging & restoration, community shared facilities and building positive relations;

- Enabling thriving and peaceful communities; and

- Celebrating cultures, diversity and inclusion.

- Note ‘will also deliver significant peace and reconciliation benefits locally.’

- Potential SEUPB support in developing plans:

- SEUPB appoint consultants soon to review community planning models; develop a model for Peace Plus; provide support materials and guidance; help facilitate development of plans to ensure consistency and guide on governance.

- Exploring ways to provide ‘direct support’ to councils / co-design.

- SEUPB exploring how to ‘ensure a seamless progression from PEACE IV to PEACE Plus’. They will be seeking CEO suggestions on this.

Investment Area 1: Co-designed Local Community Peace Action Plans Specific Objective: Peace and Reconciliation PEACE PLUS Local Community Action Plans: Sue made the group aware that Action Plans will be produced for each of the 17 local authority areas across the Programme area. These will be designed to complement the community planning structures adopted across the Programme area. The overarching plans will comprise component localised plans for defined local areas, which collectively extend to all parts of the individual local authority district. The Co-designed Local Community Action Plans will enable diverse partnerships to establish priority actions for their local areas and collectively address these, in a manner which will make a significant and lasting contribution to peace and reconciliation at the local Programme area level. Catherine raised concerns over the need to look at funding for organisations that work over all the DEAs within the DCSDC area. Sue added that this would need to be looked into maybe having a thematic system approach. Anne asked about the timeframe for PEACE Plus starting and Sue replied that timeframe has not been provided yet that it will go to public consultation first; then governmental approval, then EU sign off before councils would be able to apply. Then there would be a time lag in reaching LOO stage. In other words, a significant gap between programmes.

4. Update from Children and Young People Steering Group

4.1 Key issues:

Sue explained that this CYP theme is still making progress but is probably the one with most concerns at this point due to the fact that it was farthest behind at the start of Covid impact. PIV Team have recommended to relevant DCSDC project/line management that a change request is submitted to use the disallowed underspend already on EMS in salaries for 1 month extension of post as projects are likely to run to the wire. Latest lockdown has further impacted delivery.

4 Contract Change Requests (since November) requiring board approval:

| NW Ministry of Youth – Youth Voices | Cooperation Ireland and EA | SLA (sub-tender) | 2nd change request. After worskhops with the youth ministers and market research, App was deselected as the best route to promote NWMY. Merchandise promoted through school selected as best route to raise awareness. Request to change budget to £7,500 merchandise instead of App & residential. | Approved (some minor caveats) |
| --- | --- | --- | --- | --- |
| Participation and Democracy: Let’s Talk Gender Identity | DCSDC / Rainbow Project | SLA – Tender sub-contract | Request to reduce hours to 16 (or less) so that 113 participants will be able to be counted and project closed. | Pending since 3-12-20 |
| ARCH (Cross-Community Youth / Children) | NWCP | Tender | Adjustments to Cross-Comm youth to get final stage of project over the line – drop in hours to 16 for participants recruited from Sept 20 onwards, geographical expansion of lots to include all of Donegal, youth age expand to 11-14 instead of 12-14 | Pending since 15-12-20 Clarifications replied to on reducing hours. |
| C&YP PEACE IV Officer Extension Request | DCSDC C&YP Team | SLA | Post previously extended to end March 2021. Due to disallowed/underspend funding is already available under salary line on EMS to extend 1 further month. This will allow wrap up of projects likely to run to the wire on 31st march 21. | Pending. 8-1-21 Requires higher authority. |

Recommendation for decision: Board comment / approve changes to project delivery.

Decision: Board approve the change requests for the CYP theme.

Proposed Alison Wallace   Seconded:  Gerry Deeney

4.2 Project Officer Update:

Caitriona provided an update on her CYP projects advising that she has a meeting set up with In Your Space this week to see how to take the project forward due to the new Covid restrictions.  Caitriona also noted that she is meeting HURT to resolve their problem with recruitment of participants and added that the reimaging project in Strabane is not going to be facilitated online with the 1st test group starting soon.

Sue explained whilst still progressing well, there are individual projects which are now a risk. Due to impact of most recent lockdown, the potential picture on underspend is unclear. Board may need to review more comprehensively in March.

5. Update from Shared Spaces and Services Steering Group

5.1 Key issues:

Sue highlighted that overall this theme is looking OK on most aspects. Key concerns/risks are the Riverine and St Columb’s Park House capital projects. DCSDC has still not presented the design for phase 2 St.Columb’s Park so the timescale on completion by March 2021 is not clear. PEACE IV team have urged progress and information.

Sue advised on a potential make-or-break issue £80K on Castlederg Capital Project is still not resolved despite DCSDC presenting significant clear information. PIV Team did intensive support work Nov/Dec to get the PEACE Tourism project to completion.

1 Contract Change Requests (since November) requiring board approval:

| Project | Delivery Agent | Contract Type | Key Changes | Approval by SEUPB |
| --- | --- | --- | --- | --- |

| Castlederg Capital | DCSDC | SLA | Request in terms of £80K – procurement advise sought to avoid underspend. | pending |
| --- | --- | --- | --- | --- |

Recommendation for decision: Board comment / approve changes to project delivery.

Decision:  The Board approved the change requests for the SSS theme.

Proposed Alison Wallace        Seconded:  Gerry Deeney

5.2 Project Officer Update:

Project Officers gave a brief update highlighting key progress and concerns. See traffic lights. MaryClaire added in relation to the Castlederg project we are still waiting on a response from SEUPB.  MaryClaire explained that for the St Columb’s Park house project they are hoping to extend their current contractor because time is limited. Alison provided an update on the Waterside Partnership Shared Village project highlighting that they are just closing down the project. In relation to their Interface project for Irish Street and the Top of the Hill Alison noted that they are just to finish of the artwork.

6.  Update from Building Positive Steering Group Meeting

6.1 Key issues:

Sue explained that there has been good progress within this theme but with variation and tight deadlines on many projects to complete by March 2021.

Sue noted key risks – STEP (Advising Diversity) may give up/timescale/underspend, Gaslight Small Grant has not moved online, sport (governing bodies not available to run essential courses due to Covid/Furlough), possible underspends on some small grants difficult to determine at present especially with impact of most recent lockdown. Board may need to review position in March 2021 on some of these.

6 Contract Change Requests (since November) requiring board approval:

| Project | Delivery Agent | Contract Type | Key Changes | Approval by SEUPB |
| --- | --- | --- | --- | --- |

| Riverine | DCSDC | SLA | Request to extend project deadline to complete Environmental Action Plan and avoid having to hand back already allocated salary. | Approved |
| --- | --- | --- | --- | --- |
| Playhouse – Proud to Be | Playhouse (NW Play Resource Centre) | Small Grant | Budget heading change – to move money out of Technician salary into Director/Producer as Technician was furloughed and D/P took on extra work. | Approved |
| Minority Inclusion – Beyond Training/Capacity Building | Holywell Consultancy | Tender | Extend deadline to 28th February 21 to potentially allow for socially distanced final event/online combination. Request to reduce contracted hours to 16 for a small number of participants in exceptional circumstances. | Pending 8-12-20 End date approved. Reduction in hours – sought clarification. Group to reply. |
| Riverine | DCSDC | SLA | Final celebration event be done by recording video of each tender, reduce contact hours to 26 if required due to restrictions. | Dec 20 Pending |
| Sports | DCSDC | SLA | Extend deadline for Sports Governing Body element of training as the Sports governing body have furloughed the key trainers so it is impossible to deliver at this point. Also enable a mix of online and socially distanced delivery for other elements. | Approved |
| PUL Engagement Programme | LBF | Small Grant | Request to adjust final phase of delivery to work with Castlederg and Strabane band (adjustable to online/socially distant) and final celebration event. | 6-1-21 Pending |

Recommendation for decision: Board comment / approve changes to project delivery.

Decision: The Board approved the change requests for BPR theme.

Proposed Alison Wallace     Seconded Catherine Cooke

6.2 Project Officer Update:

Project Officers both gave a brief update on positive progress and key risks of their projects. See traffic lights. Fiona provided further detail on the Sports project explaining the need for an extension due to many of the staff required for this project are now on furloughed until end March 2021.  With the coaching qualification necessary to be delivered face to face they cannot complete this element online.

7. Meeting Closing

7.1  Any Other Business

Steelstown one of the PEACE IV Small grants projects may be handing back 20k of their overall funding.  Steelstown will provide us with more information and we will bring this back to the Board for discussion in March 2021.

7.2  Review of Actions

Action Agreed: As the meeting was not quorate, those present agreed that the minutes from 10th November 2020 and decisions taken at this meeting should be circulated to all Board members so that written responses could be noted to take the decisions to a quorate level.

Recommendation for decision: Board comment / approve changes to project delivery.

Decision: Board approve the change requests for the CYP theme.

Proposed Alison Wallace   Seconded:  Gerry Deeney

Recommendation for decision: Board comment / approve changes to project delivery.

Decision:  The Board approved the change requests for the SSS theme.

Proposed Alison Wallace        Seconded:  Gerry Deeney

Recommendation for decision: Board comment / approve changes to project delivery.

Decision: The Board approved the change requests for BPR theme.

Proposed Alison Wallace     Seconded Catherine Cooke

7.3  Date of Next Meeting  10am Tuesday  9th March 2021

Board Report.

Programme Manager for PEACE IV. Board Meeting Tuesday 9th March 2021

1. Meeting Opening (Chair Alison Wallace / Co-Chair Cllr Martin Reilly)

1.1 Welcome/Apologies (Chair/Co-Chair)

Note, quorum is 11.

1.2 Declarations of Interest (Chair)

Taken as standing declarations with project now well beyond procurement and some ended: Maureen Hetherington – Patriarchy; Unheard Voices; Minority Inclusion (capacity tender)

Catherine Cooke – Patriarchy;

Allison Wallace – Interface Investment Programme; Waterside Shared Village

Anne McTaggart – Marginalised Young Adults

Derek Moore – Cross-Cultural Strategic Initiative

Agnieszka Luczak – Cohesive Neighbourhoods Minority Inclusion

1.3 Minutes of previous meeting / Matters arising (Chair)

Recommendation: November Minutes need proposed and seconded.

2. Update from Peace IV Secretariat

2.1 PIV Team March Update (Sue):

- Overview: Team working to close down the programme. Overall position is that claims and evaluation/monitoring are now being received rapidly from groups. Team are working hard to process this but also to spot where issues are. Forecasting and underspend exercise completed. Series of requests sent to SEUPB to resolve as many issues as possible.

- Communication with SEUPB: Case Officer and Finance Officer in SEUPB overwhelmed with volume of work. Both communicating as best they can and resolving issues/updating with PIV team. Further EMS modifications needed based on recent approvals. Team has continued to work on Claims, Audits, FLC’s and LP reports.

- Forward Focus: Next quarterly claim is due at the end of April 21. Jennifer leaves post temporarily in May (and will be sorely missed). End March/early April will reveal more clearly where we’ve reached and what remains to be done. Potential closing event end May/Early June. Some DCSDC projects will be ongoing but community projects will have ended and we’ll lose audience if we leave it later. Statistics will run off early April and independent evaluation complete by end June.

2.2 Finances Update and Underspend proposals (Sue/Jennifer)

- No further FLC since January Board. FCU in SEUPB have massive workload.

- Claim 20 (due end April 21) should be significant.

- Some financial claims inevitably will fall into Claim 21.

- Details of monies owed are below in first table. Detail of forecast underspend in second table. Underspend to be discussed with Board.

| Claim | £ Owed | Submission date: | Audit update: |
| --- | --- | --- | --- |
| Claim 18 | £273,352.63 | 3rd Nov 2020 | CYP £117,208.54 Audit sample returned. All queries responded to. Waiting for FLC. LP to do SSS £50,891.69 Audit sample returned. LP to do BPR £105,252.40 Audit sample returned. LP to do |
| Claim 19 | £329,062.63 | End Jan 21 | BPR = £101,583.46 (Claim not yet sampled) SSS = £154,631.41 (Claim not yet sampled) CYP = £72,847.77 (Claim not yet sampled) |
| OWED: £602,515.26 |  |  |  |

| Period | CYP | SSS | BPR |
| --- | --- | --- | --- |
| Period 20 (01/01/21 - 31/03/21) | £118,554.61 | ​£153,739.46 | ​£142,374.19 |
| Period 21 (01/04/21 - 30/06/21) | £104,417.90 | £156,589.23 | £206,520.59 |
| Period22 (01/07/21 - 30/09/21) | £89,056.83 | £163,498.67 | £204,788.41 |
| Underspend to be reprofiled through Covid requests | £57,639.45 | £9,402.11 | £75,173.62 |
| TOTAL | £369,668.79* | £483,229.47** | £628,856.81*** |

Approach to underspend has been to seek route of minimum procurement complexity and maximum relation to existing programme to meet outputs. Programming ‘in house’ beyond 31st March 21 is managed by DCSDC as evaluation and monitoring will close systems at end March 21.

*Underspend options have been explored comprehensively with C&YP Team. Proposal is with SEUPB to extend 3 existing projects to June 21, extend salary to end August 21, introduce 3 new programming elements in existing projects to help meet outputs and spend.

**Underspend is minimal under SSS. Tourism and Bonfires minor underspend. Proposal with SEUPB to use for salaries – dependent on 12% rule on programmes/staff ratio.

*** Underspend is significant. Arises largely from Small Grants. Proposal being worked will involve additional spend on Riverine (£34K) as staff member is in post to August. Possibly extend 3 staff to end December (£42K) Detail in BPR and Appendix C.

Recommendation: Board can review and comment. Board should specifically comment on approach to underspend – noting that SEUPB have been asked in principle on elements of this (SSS and BPR) and have received specific detailed request in relation to C&YP theme.

3. Update on Operational Work Plans

3.1 Workplan 1: Project Mobilisation/Management (Sue)

Official Extension: Our programme now runs to end September 2021. SEUPB Management Authority can extend to Dec 21 without significant issue. We’ve queried whether some underspend can go into salaries and how that works with the 15% rule.

Start and End surveys: Summarised below. Note figures DO include duplicates after May 2020. Rapidly changing – significant progress ongoing.

| Theme | 4-1-21 Start Surveys | Start (23-2-21) | 4-1-21 End Surveys | End (23-2-21) | Overall Target | Cross-Comm Balance CNR/PUL/Other |
| --- | --- | --- | --- | --- | --- | --- |
| C&YP | 2224 (108%) | 2956 (143%) | 1088 (53%) | 1862 (90%) | 2060 | 53%/28%/19% |
| SS&S | 1632 (130%) | 1683 (133%) | 1041 (83%) | 1150 (91%) | 1260 | 55%/26%/19% |
| BPR | 2248 ( 145%) | 2284 (147%) | 1364 (88%) | 1454 (94%) | 1548 | 45%/30%/25% |
| TOTAL: | 6104 (125%) | 6923 (142%) | 3493 (72%) | 4466 (92%) | 4868 | 51%/28%/21% |

Traffic Lights: Updated payments, progress, and participant numbers. Areas in red are of concern.

Independent Evaluation: Rubicon have completed questionnaire with projects, 5/15 case studies. Agreed 6th May as date for feedback on first draft of report to projects and board and staff.

Statistics/Evaluation and Monitoring: PIV Manager dealing with as many of the anomalies and as much of the reporting as possible. Possibility of 10% uplift on Rubicon contract to cover some additional use of final statistics given that NISRA turned down role. All evaluation and monitoring must be completed by end March.

Recommendation: Board confirm in principle if content that a request be sent to SEUPB for the programme be extended to end December if necessary for closure purposes. Board requested to put 6th May in diaries for Feedback from Evaluation. Board may wish to consider when it formally ends.

3.2 Workplan 2: Communications (Sue)

Final Closure Event: Have talked with SEUPB. Their requirements are minimal. Their Communications team will seek video and/or quote from Gina Hegarty and sponsoring Departments. We will issue a press release, put the 3 videos on the web. Suggestion that we run 1 final ‘live’ event on zoom. Format – Welcome, video/statement from SEUPB CEO, 3 thematic videos, some feedback from independent evaluation, some consideration of Peace Plus. Suggestion of end May/early June event.

Communications with projects: Continuing emails to projects promoting key messages

Press: Projects issuing final press releases. PEACE IV press release at closing event.

E-newsletter: No further e-newsletters have been issued due to staff workload.

Magazine: One final magazine to be written and issued – predominantly should be a celebration of achievements and summary of the evaluation. May look ahead to Peace Plus.

Recommendation: Board to consider communications – in particular format/date for end event.

3.3 PEACE PLUS Update

There has been no communication to PEACE IV managers on Peace Plus. It is known that SEUPB has a £250K tender out for contractor to develop 17 local authority plans. Deadline for that application was 22nd February 21. Work is to be complete November 21. If that timescale was kept, it might mean LAP’s submitted early 2022. Probably 6-9 month approval like before? Money potentially not on the ground until late 2021/2022?

Action plans will be produced designed to complement the community planning structures. As cross-community targets and hours appear to potentially still be included and as each structure must represent diversity, this will provide interesting issues and opportunities in our demographic. Suggestion is that at the next Board meeting, when hopefully most of our programme is closed, Board should consider available information on Peace Plus.

Recommendation: Peace Plus to be kept on the agenda for the next Peace IV Board meeting.

4. Update on Children and Young People Work Plan

4.1 Key issues (Sue):

With potential £57,639.45 underspend, Chair and Co-Chair of Board and SRO of programme were approached in February and decision agreed in principle that SEUPB should be approached with Covid Change requests taking programming delivery beyond end March. PIV Team have worked with CYP Officer & Community Services and a series of request changes presented to SEUPB which will successfully conclude all elements of programming, expenditure and claims by end August 2021. Awaiting response from SEUPB on more recent or complex requests.

9 Contract Change Requests (since January) requiring board approval:

| Project | Delivery Agent | Contract Type | Key Changes | Approval by SEUPB |
| --- | --- | --- | --- | --- |
| Pilot Youth Zone | Youth Zone Steering group | Glen Devpt Initiative SLA (sub-tender) | Extension to 31st March 21 Reduction in hours for one cohort – 16 hours requested for 26/60 young people. Delivery via zoom for remainder of project. Includes field trip now virtual and merch as an incentive for participation now trip cancelled. | Yes (no on some elements of merchandise) |
| Pilot Youth Zone | Youth Zone Feasibility Study and Business Case | S3 Solutions SLA (sub-tender) | Extension of end date to 31st March 21. Delivery of final elements online. | Yes |
| Youth Participation and Democracy | North West Ministry of Youth | Co-operation Ireland SLA (sub-tender) | Number of participants reduction from 35 to 20 Reduction in hours from 26 to 16. Delivery of project switching to online. | 15-1-21 |
| Take Back the Streets | DCSDC | SLA subcontracted to In Your Space | To request meeting only 85% of contracted participants but being allowed full payment. To request 48 participants can complete with 16+ hours of contact time. | 5-2-21 |
| NW Ministry of Youth | DCSDC – sub tender EA/Cooperation Ireland | SLA | Request to use final spend on wellbeing and GR packs for participants | 24-2-21 |
| Love the life you live | HURT | SLA sub-tendered | Extend to 30th June. Reduce target from 200 to 100 participants and return half of budget. (£29,423.50) | 3-3-21 |
| Changing Forms | DCSDC | SLA | Extend to 30th June. Will complete 120/150 participants. Reduce threshold hours to 16 (possibly 21). Return £9k of budget into alternative programming | 3-3-21 |
| Youth Street Art | DCSDC | SLA | Extension of end date to 30-6-21. Will complete with existing participants and recruit 15 more. Mosaic installation in Strabane Canal Basin. | 3-3-21 |
| Salary & additional programming | DCSDC | SLA | Salary extension to end August 21 (£14,941.67 from programmes). To close off all paperwork/claims on CYP project as projects now run to 30-6-21. Officer will also use £43,964.89 underspend/reprofiling for additional projects to meet CYP targets (Mind Body Soul – 100 participants 16hrs; Reimaging Derry youth street art 20 participants 16 hrs; Be The Voice 10-15 participants 16 hrs). | 3-3-21 |

Recommendation for decision: Is Board happy with approach to underspend submitted to SEUPB? Board comment / approve changes to project delivery subject to SEUPB approval.

4.2 Project Officer Update: (Caitriona, Mary Claire & Fiona):

Project Officers will both give brief updates. See traffic lights.

Recommendation: Board to consider and give any comments.

5. Update from Shared Spaces and Services Steering Group

5.1 Key issues (Sue):

With only a predicted underspend of £9,402.11 this theme is doing well. The capital projects however have had to be extended, causing the need for overall programme extension to September 2021, and possibly further.  Note however that no programming aspects are going beyond 31st March 2021. Querying SEUPB if underspend can be used to PIV Team salaries.

5 Contract Change Requests (since November) requiring board approval:

| Project | Delivery Agent | Contract Type | Key Changes | Approval by SEUPB |
| --- | --- | --- | --- | --- |
| Peace Tourism | DCSDC | SLA | Extension of deadline to end February. To allow for purchase of marketing/promotional materials for City of Peace Brand and to spend final elements of budget. | Yes |
| St.CP Walled Garden | DCSDC | SLA | Extension to Sept 2021 to complete capital element only – all other elements to be completed by end March 21 | Yes |
| Castlederg | DCSDC | SLA | Extension to Sept 2021 to complete capital element only – all other elements to be completed by end March 21 | 8/2/21 |
| Shared Space Strabane | Holywell | Tender | Asking for a small number of participants to be counted at 16 hours. | 22/2/21 |
| Shared Space Newtownstewart | Dennett | Tender | Asking for extension to end March 21 and taking final event online | 22/2/21 |

Recommendation for decision: Board comment / approve changes to project delivery subject to SEUPB approval and any comments they wish to make on underspend.

5.2 Project Officer Update: (Mary Claire & Fiona):

Project Officers will give brief updates highlighting key progress and concerns. See traffic lights.

Recommendation: Board to consider and give any comments.

6. Update on Building Positive Relations Work Plan

6.1 Key issues (Sue):

With predicted underspend of £75,173.62 this theme requires thought as to what is possible/permissible under SEUPB regulations. Underspend comes predominantly from Small Grants (many with a few thousand each of underspend and some, like Steelstown GAC handing back c. £26K). STEP Advising Diversity has also decided not to complete project. Gaslight have been hard to reach to get decisions on potential changes.

SEUPB have been asked in principle if they would consider a Covid Change Request in relation to £42K towards extending 3 of the PEACE IV Team salaries to end Dec 21 and the remainder (c.£34K) being a Covid Change Request in under Riverine for additional programming related to legacy and sustainability of the Environmental Action Plan. The Riverine Officer is in post until August 2021 and the project is managed by DCSDC. We also think the DCSDC sports led project (which requires outdoor training programmes as a critical part of delivery) will need extended into the Autumn. Details are in the appendix. This adds further justification to needing PIV Team salaries extended. The salaries request for PIV team would take us beyond the 15% proportionality rule on the programme so it’s not clear what SEUPB will say. Other council’s have indicated SEUPB have linked salaries extensions to specific projects – possibly to get around this.

4 Contract Change Requests (since January) requiring board approval:

| Project | Delivery Agent | Contract Type | Key Changes | Approval by SEUPB |
| --- | --- | --- | --- | --- |

| People Always Ask Us | Playtrail (Liberty Consortium) | Small Grant | Extend to 31st March. Instead of final celebration do photo books, hoodies, visual display. |  |
| --- | --- | --- | --- | --- |
| Creative Centenaries | Nerve Centre | Tender | Requesting that a small cohort of 13 participants be allowed to count at 18 hours. | 22/2/21 |
| PEACE IV Project | Playhouse | Small Grant | Request to reduce from 37 hours to 26 hours | 24/2/21 |
| Epilogues | Gaslight | Small Grant | Pending request at time of issuing Board Papers – verbal update. Likely request for cohort 2, 9 participants to count at 16 hours. Remainder of programming to be delivered online. Will reduce underspend and allow project to meet audit level on targets for payment. | To be submitted |

Recommendation for decision: Board to comment on plans in principle for usage of underspend subject to SEUPB approval and to comment / approve changes to project delivery.

6.2 Project Officer Update: (Mary Claire & PIV Team):

Project Officers will both give brief updates on positive progress and key risks. See traffic lights.

Recommendation: Board to consider and give any comments.

7. Meeting Closing (Chair)

7.1  Any Other Business

7.2  Review of Actions

7.3  Date of Next Meeting  10am Tuesday  11th May 2021 (See appendix A)

APPENDIX A:  PEACE IV Timetable for Board & Steering Group 2020/21

|  | Sept | Oct | Nov | Dec | Jan 21 | Feb 21 | Mar 21 | Apr 21 | May 21 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEACE IV Board | 8 Webex |  | 10 Zoom |  | 12 Online |  | 9 |  | 11 |
| Children & Young People | Suspended for remainder of programme due to Covid |  |  |  |  |  |  |  |  |
| Shared Spaces and Services | Suspended for remainder of programme due to Covid |  |  |  |  |  |  |  |  |
| Building Positive Relations | Suspended for remainder of programme due to Covid |  |  |  |  |  |  |  |  |
| Operational | Suspended for remainder of programme due to Covid |  |  |  |  |  |  |  |  |

Appendix B: Historic Attendance record at board meetings. (*Joined at later date)

| Elected Representatives | 12/19 | 2/20 | 4/20 | 5/20 | 6/20 | 9/20 | 11/20 | 1/21 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cllr Raymond Barr (Ind) | N/A | N/A | N/A | N/A | N/A | A | A | A |  |  |
| Cllr John Boyle (SDLP) | N/A | N/A | N/A | N/A | N/A | A | P | A |  |  |
| Cllr Sandra Duffy (SF) | A | A | A | P | P | P | P | A |  |  |
| Cllr Steven Edwards (SDLP) | N/A | N/A | N/A | N/A | N/A | A | A | A |  |  |
| Cllr Christopher Jackson (SF) | P | P | A | P | P | P | P | A |  |  |
| Ald Hilary McClintock (DUP) | A | A | P | P | P | P | A | A |  |  |
| Cllr Ruairi McHugh (SF) | P | A | A | A | A | P | P | A |  |  |
| Cllr Philip McKinney (AP) | A | P | A | P | P | P | A | A |  |  |
| Cllr Aileen Mellon (SF) | N/A | N/A | N/A | N/A | N/A | A | A | A |  |  |
| Ald David Ramsey (DUP) | N/A | N/A | N/A | N/A | N/A | A | A | A |  |  |
| Cllr Martin Reilly (SDLP) | P | P | P | P | P | P | P | A |  |  |
| Cllr Brian Tierney (SDLP) | A | A | A | A | A | A | A | A |  |  |
| Statutory Partners |  |  |  |  |  |  |  |  |  |  |
| Ms Dairine McGarrigle (DOC) | A | P | A | A | P | A | P | A |  |  |
| Elizabeth Campbell (WHSCT) | P | P | A | P | P | A | A | A |  |  |
| Kathleen McCaul* Or Gillian Moss (NWRC) | A | A | A | A | A | A | P | P |  |  |
| CI Rosie Thompson (PSNI) Jonathan Hunter/ Robin Blair | P | P | P | P | P | P | A | A |  |  |
| Mr Gerard Deeney (NIHE) | P | P | A | A | P | P | A | P |  |  |
| Stephen Quigley (EA) | A | P | P | A | A | A | A | A |  |  |
| Social Partners |  |  |  |  |  |  |  |  |  |  |
| Catherine Cooke (FWIN) | A | P | A | P | P | P | P | P |  |  |
| Paul Gallagher (TU) | A | A | A | A | A | A | P | A |  |  |
| Maureen Hetherington (Junction) | A | A | P | P | P | P | P | A |  |  |
| William Lamrock (YMCA) | P | P | A | A | A | A | P | A |  |  |
| Agnieska Luczak (Polish Abroad) | P | P | P | P | P | A | P | A |  |  |
| Wendy Gibbons (OWNR) | N/A | N/A | N/A | N/A | P | P | A | P |  |  |
| Margaret McLaughlin (Dennet) | A | P | A | P | A | A | A | A |  |  |
| Anne McTaggart (YouthAction NI) | P | A | A | A | P | A | P | P |  |  |
| Derek Moore (LBF) | P | P | P | P | P | P | P | P |  |  |
| Teresa Stewart (Strabane A.Y.E) | P | P | A | A | A | A | A | A |  |  |
| Alison Wallace (WNP) | P | P | A | A | A | P | P | P |  |  |

Appendix C – Summary of Riverine Proposal.

Riverine- All Together Project [working title]

Name: Riverine- All Together Project is an extension to the Riverine Environmental Project which was successfully delivered during 2020/21.  Within these projects an emerging Environmental Action Plan is being developed- Strabane and Lifford Environmental Action Plan (SLEAP). This extension project will help animate the action plan.

Relevance to Riverine Capital Project: Both of these projects have been designed to help engage different communities with the Riverine Community Park capital project. However, it is recognised that their impact has the potential to do a lot more. By engaging in these types of environmental activities participants are aware that nature does not recognise barriers or borders and that we all have a shared responsibility to become environmental stewards.

Environmental Action Plan: Through the mapping and stakeholder/community engagement we will identify priorities for action in the area, including actions for statutory/public agencies, for voluntary organisations and for communities. The aim will be to have a 1-year plan and mid- and long-term objectives, in a compact, attractive document that can be reviewed and updated annually.

Participation Targets: This project has a target of up to 60 participants (min 16 hours over a minimum of 3 months).

Project area: The project area will remain the same as the initial project- roughly 12km from the Strabane/Lifford bridge, taking in a range of communities as shown below. This is not an absolute boundary, and worthwhile projects outside the project area will be considered.

How the extension project differs from the initial Riverine Environmental Project:

Riverine Environmental Project consisted of 3 parallel programmes (Environmental Champions, Environmental Explorers & Learning in the Landscape). The concept behind the extension project is that it will amalgamate these programmes together. Whereas before the programmes focus was relatively concentrated on learning, exploring or practical action this project will merge these together. The programme delivery will take into account all 3 elements.

Implementation

Delivery: The project activity will be run from May 2021 to July 2021, procured through knowledgeable and experienced local providers. As well as ensuring sustained and meaningful contact between communities, this project will be designed to have a sustainable environmental legacy supported by identified statutory and voluntary sector organisations, and have direct links to the development of the Riverine Community Park.

Steering Group: The original Riverine Environmental Project steering group will be asked to remain. They will meet once a month to discuss aspects of the project. Relevant, new members will have the opportunity to join.

Initial Community Engagement: An extensive community engagement process was carried out initially with the Strabane/Lifford and hinterland areas, to raise awareness of the programme and ensure community buy-in.

Programme: Participants will have the opportunity to engage with all elements of the project on a rotation basis. Joint sessions with a shared base will be considered.

The elements will have a primary focus; however, they must take into account the 3-pronged approach of Learning, Exploring and Doing.

LEARN MORE: A programme based around the notion of learning to live more sustainably.

-To include foraging, home growing skills and sustainable life hacks.

EXPLORE MORE: An active travel programme that takes participants off the beaten track to locations that are not often explored.

-To include the identification and mapping of pollution/ litter hotspots.

DO MORE: A programme of practical work days to improve the environment.

-To include clean-ups and environmental improvement works.

Final Celebration Event: This event will be a chance to celebrate the successes of both projects and an opportunity to plan and to look at how the environmental action, and the links between communities can be carried on in the future.

Sustainability: The combination of both these projects will leave a legacy of specific skills and capacity in the local area, and a framework for the strategic management of the environment. It will also leave a socially sustainable legacy of improved relationships between different identities (PUL/CNR/BME) and contribute to a change in perceptions about Protestant alienation from the Strabane Town area, which will have economic as well as social impacts.

Covid 19 Planning: Covid-19 protocols will be continued, including social distancing measures and increased hygiene. Participants must be able to assemble at the agreed locations by means of their own transport. Suitable locations must be chosen to allow for these measures.

Budget:

60 participants with 16hours engagement @ £480 per participant = £28,800

Further budget will be spent on developing an environmental toolkit library.